# SHARKS STUDENT HALL CONSTRUCTION PROJECT
## Project Overview and Initiation Phase
### Project Overview
The Student Hall Construction Project at Kyambogo University aims to build a modern, safe, and affordable accommodation facility for students at the university. This initiative addresses the critical shortage of on-campus accommodation that has forced many students into overcrowded halls and expensive private halls.
### Problem Overview
Currently, many students live far from campus, endure long commutes, and spend excessively on rent. The shortage of hall space leads to stress, reduced academic performance, sanitation and safety concerns. Hence, the university decided to undertake a project managed by Sharks Project Managers and Consultants to construct a 500-bed capacity hall to improve students’ living conditions and academic success.
### Objectives
- Construct a fully functional student hall within 48 months.
- Provide affordable, quality, and safe accommodation for at least 500 students.
- Equip the hall with modern services: water, electricity, internet, and sanitation.
- Enhance student welfare and academic concentration.
### Scope
The project covers:
- Building design and construction.
- Installation of utilities (electricity, plumbing, Wi-Fi).
- Interior furnishing and landscaping.
- It excludes hall management and maintenance after handover.
### Alternative Approaches
Option	Description	Assessment
A	Renovate existing halls	Limited space
B	Partner with private hostels	Unsustainable
C	Construct new hall	Preferred, sustainable

### Prefeasibility Study (PESTEL Analysis)
Factor	Issues	Implications
Political	Government promotes education infrastructure	Easier approvals
Economic	Inflation and cost fluctuation	Budget sensitivity
Social	Increasing enrollment, rising housing demand	Strong justification
Technological	Modern construction methods	Faster and safer build
Environmental	Construction waste and noise	Must comply with NEMA
Legal	Land ownership, permits	Requires legal clearance from KCCA, MoES, MoWT, etc

### Initial Estimates and Risks
- Cost: UGX 4.2 billion
- Duration: 48 months
- Risks: Cost overruns, contractor delays, permit and regulatory challenges.
## Preparation and Planning Phase
This phase defines the foundation for execution through detailed planning, budgeting, and scheduling.
### Resource Baseline
Resource	Description
Human	Skilled & unskilled labour
Material	Construction inputs
Financial	Capital requirement
Equipment	Site machinery

### End Product Quality Standards
The hall will meet National Building Codes and ISO 9001 standards emphasizing:
- Safety, durability, and comfort.
- Reliable utilities and accessible facilities.
- Fire safety and environmental sustainability.
### Project Master Plan
The master plan outlines the Work Breakdown Structure that includes timeline, and deliverables.
1. Site clearance
2. Foundation
3. Structural works
4. Roofing
5. Finishing and furnishing
6. Inspection and handover
### Project Policies and Procedures
- Procurement: Competitive bidding process.
- Safety: Personal Proctective Equipment enforcement and regular inspections.
- Communication: Weekly meetings and progress reports.
- Environmental: Waste recycling and low-emission materials.
### Institutional Arrangements
Supervised by the University Estates and Works Department and managed by:
- Project Manager (Sharks Project Managers and Consultants)
- University Engineer
- Contractor Representative (From ROKO Construction Limited)
- Finance Officer (University Bursar)
- Student Affairs Representative (Guild President)
### Financial Plan Before Securing Funds
Source	Contribution
University Capital Budget	41%
Donor & Alumni Support	30%
Bank Loan	29%

### Appointment of Key Members
Key appointments include:
- Project Manager — For overall coordination
- Quantity Surveyor — For cost control
- Architect — For design compliance
- Safety Officer — For site health & safety
- Clerk of Works — For on-site supervision
## Project Implementation Phase
The implementation phase involves the actual construction activities, ensuring plans are executed according to design, budget, and timeline.
### Key Construction Activities
1. Site Preparation: Land clearing, fencing, and leveling.
2. Foundation Works: Excavation and concrete pouring.
3. Superstructure: Walling, beams, columns, and roofing.
4. Finishing: Plastering, painting, and tiling.
5. Utilities Installation: Plumbing, electricity, internet(Eduroam), and fire systems.
6. Furnishing and Inspection: Furniture setup and safety testing.
### Monitoring and Evaluation
Project progress is tracked through:
- Weekly site reports and visual inspections.
- Budget monitoring by comparing actual vs. planned expenditure.
- Weekly site meetings.
- Monthly performance reviews.
- Transparent financial reports.
### Risk and Change Management
- Potential Risks: Inflation, weather delays, labour shortages.
- Mitigation Measures: Contingency funds, contract penalties, early procurement.
  Any proposed design or budget change must go through the Change Control Process.
### Quality and Safety Assurance
- Routine inspections by engineers.
- Material testing for compliance.
- Workers should be equipped with Personal Project Equipment and trained on safety practices.
## Evaluation and Termination Phase
### Project Evaluation
Evaluation ensures that project outcomes align with initial goals in terms of time, scope, cost, quality, and stakeholder satisfaction.
#### a) Performance Evaluation
- Compare planned vs. actual completion time and cost.
- Calculate Cost Performance Index (CPI) and Schedule Performance Index (SPI).
#### b) Outcome Evaluation
- 500 students housed comfortably.
- hall operational within budget and time.
- Student welfare and academic performance improved.
#### c) Impact Evaluation
- Improved university image and safety.
- Reduced off-campus housing costs by 25%.
- Boosted student satisfaction and enrollment rates.
### Termination and Handover
1. Final Inspection: Certify completion and compliance.
2. Handover Ceremony: Transfer facility to University Estates Department.
3. Documentation: Archive blueprints, contracts, and reports.
4. Post-Implementation Review: Conducted 6 months after handover.
5. Demobilization: Release of temporary staff and closure of contracts.
### Lessons Learned
- Early stakeholder involvement enhances project acceptance.
- Accurate budgeting and strong risk management prevent delays.
- Clear communication sustains transparency and trust.
- Continuous quality control ensures long-term building durability.

## 1.b
## Stakeholder Management Process
Stakeholder management ensures all parties involved in or affected by the project are properly identified, engaged, and managed throughout the life cycle.
### Stakeholder Identification
Category	Stakeholder	Interest/Influence
Internal	University Council	Approval and oversight
Internal	Project Team	Execution and monitoring
Internal	Students	Affordable and quality accommodation
External	Contractors & Suppliers	Timely payment and project success
External	Local Government	Compliance with building standards
External	Funders	Accountability and transparency
External	Local Community	Environmental and noise impact

### Stakeholder Analysis (Power–Interest Matrix)
- High Power, High Interest: University Management, Project Manager
- High Power, Low Interest: Donors, Government agencies
- Low Power, High Interest: Students
- Low Power, Low Interest: Local residents
### Stakeholder Engagement Process
1. Identification: Listing all individuals or groups affected.
2. Analysis: Assessing influence and expectations.
3. Planning: Defining engagement strategies.
4. Engagement: Meetings, reports, and feedback sessions.
5. Monitoring: Reviewing stakeholder satisfaction regularly.
### Communication and Engagement Strategies
Stakeholder	Engagement Method	Frequency
University Council	Board reports	Monthly
Students	Consultative meetings, surveys	Quarterly
Contractor	Site meetings	Weekly
Donors	Financial reports, newsletters	Quarterly
Local Authorities	Permit updates	As required

### Stakeholder Monitoring
The Project Manager maintains a Stakeholder Register and uses feedback logs to track issues, satisfaction levels, and responses. Regular communication ensures cooperation, transparency, and conflict resolution.